## Sheet1
|  | Date Planned | Expected Start Date | Date Achieved | Work Planned | Work Achieved | Next Steps | Notes, challenges, special info
Sprints | 1 | 2020-01-20 | 2020-01-20 | 2020-01-20 | Module intro lecture | first impressions of the project and subprojects | read more on it
|  |  | 2020-01-22 | 2020-01-22 | Download Data | Data files downloaded | open them | how to open?
|  |  | 2020-01-23 | 2020-01-25 | Understand the project | Take notes and questions to ask later | check with teaching staff, turn into project spec
|  |  | 2020-01-24 | 2020-01-26 | Understand the subproject | A subproject was chosen visualization | choosing the tools to start working with it
| 2 | 2020-01-27 | 2020-01-27 | 2020-01-27 | Experiment with different tools (MATLAB and python) | tried some tutorials for MATLAB and watch a few videos to implement bid data in python | choose the one that feels more comfortable to work with | very unsure which to chose
|  |  | 2020-01-29 | 2020-01-30 | Understand the data models | what they are and they represent | try to visualize them | different ways of measuring ozone?
|  |  | 2020-01-31 | 2020-02-05 | Specs doc | notes and some questions | formalise text later | didn’t understand some sections. Some parts are to do later
|  |  | 2020-01-31 | 2020-02-15 | SMART targets | SMART list created | past it in report template | forgot about it
| 3 | 2020-02-03 | 2020-02-03 | 2020-02-04 | User interface schematics | diagram of the user interface | implement it on specs doc | png file
|  |  | 2020-02-05 | 2020-02-09 | Open and visualize the data (MATLAB) | files were opened in MATLAB | Plot and explore data | serves as a tool to visualize the data and the variable and help me understand the .nc file. chosen language was python
| 4 | 2020-02-10 | 2020-02-10 | 2020-02-10 | Open data and extract models with xarray | data was loaded | extract the global variables | first implemented with NetCDF, but after research xarray was used more often. So, I switched
|  |  | 2020-02-10 | 2020-02-10 | Extract and convert coordinates and time in NumPy arrays | convert code let, long and hour variables from array into a NumPy array was done | make sure there are no error, by printing sections of the np array
|  |  | 2020-02-13 | 2020-02-12 | Visualize data of NumPy arrays data in terminal | the array was printed in the terminal | plotting it | array was 4 dimension and too big. Need to slice the time to only have a matrix with the 03 values in each long ang let for a specify hour
|  |  | 2020-02-15 | 2020-02-18 | Experiment with Matplotlib |  |  | it was delayed because it was difficult to understand how the array worked and how it could be manipulated in order to print it
| 5 | 2020-02-17 | 2020-02-17 | 2020-02-19 | Create a window | window was created | plot the graph
|  |  | 2020-02-17 | 2020-02-19 | Plot model’s data in a graph | data was plotted in a graph inside of a window | set axis or overlay map | basic plotting was simple
|  |  | 2020-02-20 | 2020-02-22 | Create a graph per model in one window | data Ong the graph was changed based on the model | plot them all at once without having to change the models name in the code | slowed down the graphical creation process
|  |  | 2020-02-20 | 2020-02-24 | Positions the graphs in the window | position all graphs was set in the same windows and plotting all of them at once for just one hour | make a more efficient loop | slowed down the visualization of the graphs a lot more. Is taking 5 min
|  |  | 2020-02-23 | 2020-02-27 | Overlay map based on coordinates | map was added underneath the data and coastlines on top | set axis | the data is so much the map gets completely covered. It was delayed because there were issues to implement the right map. Module to create them had to change to cartopy. Geos wasn’t working
| 6 | 2020-02-24 | 2020-02-24 | 2020-02-27 | Create graphs axis | axis was set |  | graphs need to be repositioned since the axis changed their dimensions and positions
|  |  | 2020-02-24 | 2020-02-27 | Add tittle of each model on top of the graphs | model's title added to each graph
|  |  | 2020-02-26 | 2020-02-29 | Create a window per hour | 24 windows were created with 8 graphs in each | needs parallel processing to cut down the time | couldn’t plot it. too long of a wait
|  |  | 2020-02-28 | 2020-02-29 | Add windows title | title added
|  |  | 2020-02-29 | 2020-03-01 | Create the colorbar | colorbar created | position and set dimensions | prints colorbar in all graphs. Changed position of graphs once one colorbar per windows was achieved
|  |  | 2020-03-01 | 2020-03-04 | Position colorbar on the window | ideal position achieved | assign same colour as data | a lot so trial and error
|  |  | 2020-03-01 | 2020-03-05 | Assign colour of the graphs to the colorbar | input colour was assigned to colorbar | max ticks need to be set
|  |  | 2020-03-01 | 2020-03-06 | Set max ticks of colorbar | set max ticks to higher value |  | delayed because there was an error due to the max ticks, which prevented the graphs from plotting
| 7 | 2020-03-02 | 2020-03-02 | 2020-03-07 | Create the button | button was created
|  |  | 2020-03-02 | 2020-03-07 | Set callback | close all event was added to the button function | position of button | it might not work because is taking a lot to process the callback and the plotting in general
|  |  | 2020-03-02 | 2020-03-07 | Position the button on the window | button was positioned where the user interface diagrams sets it to
|  |  | 2020-03-06 | 2020-03-09 | Create folder on directory | if statement was coded to check if folder was already the current directory or not, if not creates it | save the images
|  |  | 2020-03-06 | 2020-03-09 | Save windows as png | window is saved on the folder with the png extension | give a simple, easy to understand name to images saved | creates 24 pngs
|  |  | 2020-03-06 | 2020-03-09 | Rename image with the hours the models represent | images are being renamed with the hour when saved |  | their go from 1 to 24
| 8 | 2020-03-09 | 2020-03-09 | 2020-03-13 | Implement parallel processing | parallel processing was implemented using concurrent.futures.ProcessPoolExecutor | input code | hard to implement. A lot of research was necessary. Code was implemented first in a small array to understand how it worked
|  |  | 2020-03-13 | 2020-03-16 | Code terminal-based inputs | user inputs were set to get the colour chosen by the user | change the graphs and the colorbar colour dynamically | Initially tried to implement it via a button, but this was not possible since the graphs need to be plotted again to change the colour.
|  |  | 2020-03-13 | 2020-03-16 | Change graphs colour | graphs colour was change for a variable to dynamically chance its colour. | errors and tests | could be dynamically set, like the colorbar because otherwise I would be able to see any plotting.
| 9 | 2020-03-16 | 2020-03-16 | 2020-03-18 | Error handling | user input error was handled | testing
|  |  | 2020-03-19 | 2020-03-25 | Testing